## Slide 1: Updating the 2004 CPI Manual
May 10, 2019
Meeting of the Ottawa Group
Rio de Janeiro, Brazil
Brian Graf
Senior Economist, Real Sector Division

## Slide 2: Background
2014 UNECE-ILO CPI Group of Experts Meeting
2014 IWGPS endorsement for updating the CPI manual
Multiple layers of review
  Substantial comments from compilers
  24 countries
  IWGPS member agencies
Two publications
  Consumer Price Index Manual: Concepts and Practices (Manual)
  Consumer Price Index: Theory

## Slide 3: Progress to date
Chapter outlines
Draft chapters
Main review
International consultation of CPI compilers and users.

## Slide 4: Progress to date
IWGPS agency review
Incorporate comments from IWGPS
Meeting of IWGPS – October 2018
Incorporate comments from compilers and users

## Slide 5
Editing for consistency (ongoing)
Outside review
Revision of chapters to include IWGPS comments
Progress to date

## Slide 6: Next Steps
Update chapters reflecting comments from outside review
Formal consultation of countries
Submission of the final manual for endorsement by the UNSC
Final approval from IWGPS

## Slide 7: Proposed timeline (Manual)
Formal country consultation – July 1 – September 15, 2019
Final draft available – October 1, 2019
Formal editing (IMF) – October 1, 2019 – February 29, 2020
White cover version submitted to UNSC – February 2020
Endorsement by UNSC – March 2020

## Slide 8: Manual
Reflect established best practice as of now
Challenge – dynamic nature of compilation methods
Guidance Notes to be issued as needed to ensure Manual remains current
  Recognize that methods continue to evolve
  Research drives development of new best practices
    Research evolves into best practice
  Guidance Notes issued to update relevant chapter in the Manual

## Slide 9: Manual
Research Agenda
  Identifies topics for further research and discussion
  Foster the development of new methodologies
  Guide the agendas for upcoming meetings of UNECE-ILO CPI Group of Experts and Ottawa Group

## Slide 10: Proposed timeline (Theory)
Draft chapters available – August 31, 2019
Review by main reviewers – September 30, 2019
Incorporate comments from reviewers – October 31, 2019
Review by IWGPS – December 31, 2019
Incorporate comments from IWGPS – January 31, 2020
IWGPS discussion on final version – February 29, 2020
Formal editing – May 31, 2020
Theory publication will not be endorsed by the UNSC

## Slide 11: Key Changes/Updates
Provide more practical advice wherever possible
Streamline – reduce unnecessary repetition
Increased harmonization with national accounts concepts
Two new chapters
  Scanner data
  Updating weighs and linking index series
Rewrites
  Sampling
    Focus on multi-stage sampling process in practice
    Practical realities faced by compilers and availability of sampling frames
  Missing prices and quality adjustment
    More detailed examples and clearer guidance

## Slide 12: Key Changes/Updates
Update and develop new detailed examples
  Missing prices, quality adjustment
Identify and summarize steps needed to develop and maintain a CPI
Streamline and combine chapters on concepts, uses, and classifications
Augment and expand use of national accounts data and alternative data sources to develop weights

## Slide 13: Key Changes/Updates
Treatment of internet purchases and collection of on-line prices
Data editing
Innovations in the collection of prices
  Web-scraping
  Hand-held computers/tablets
Theory and concepts
  Treatment of scanner data in the calculation of elementary aggregates
  Quality adjustment methods to deal with scanner data
Comments

## Slide 14
Thank you!
Comments welcome
bgraf@imf.org
mtavareslimamartin@imf.org